## Cover
DELIVERABLE B3 — 100-DAY AI INTEGRATION ROADMAP
Nordhaven–LumaPay AI Risk Task Force · Governance & Standards Contribution to Deliverable B (Technical Appendix)
Deliverable | B3 — 100-Day AI Integration Roadmap (Governance, Standards & Regulation focus)
Brief Requirement | A phased roadmap, mapped to maturity levels from initial to optimised. Include dependencies, milestones, and the specific NIST AI RMF or NIST CSF functions each initiative addresses. (Brief Slides, Deliverable B; Bıçakçı)
Systems in Scope | LumaCredit-EU · LumaAssist Chat · AutoUnderwriter Agent · FraudShield
Phase Structure | Phase 1 (Days 1–30): GOVERN — Establish ¦ Phase 2 (Days 31–60): MAP — Classify ¦ Phase 3 (Days 61–100): MANAGE — Operate. Aligned to G6 board pack (Deliverable A) and Kok, Day 3 Sess 2 (90-day plan, Slide p.36)
Initiative Count | 18 initiatives: Phase 1 = 5 (R-G01–R-G05) · Phase 2 = 7 (R-M01–R-M07) · Phase 3 = 6 (R-O01–R-O06)
Workstream Alignment | Three workstreams per Kok, Day 3 Sess 2, Slide p.36: WS1 = inventory/agent cards (Weeks 1–4 → Phase 1); WS2 = decision rights matrix and board dashboard (Weeks 5–10 → Phase 2); WS3 = first tabletop on real use case (Weeks 11–12 → Phase 3)
NIST AI RMF Functions | GOVERN (accountability, culture, policies, roles) · MAP (classify, characterise, context) · MEASURE (evaluate, test) · MANAGE (deploy, monitor, escalation). Primary source: EAIRM Framework p.7–10; Standards & Controls doc p.1–2 ⚠ Sub-function codes explicitly course-cited: MAP 1.5 (Brief Slides Closing) and MEASURE 2.6 (EAIRM §10.1). All other sub-function numbers are general knowledge from the NIST AI RMF document.
NIST CSF 2.0 Functions | Govern · Identify · Protect · Detect · Respond · Recover. Source: EAIRM Framework p.14 (Standards Cross-Reference Matrix)
Maturity Model | EAIRM five-level model (Framework p.12): L1 Ad Hoc → L2 Aware → L3 Structured → L4 Integrated → L5 Adaptive. LumaPay start: L1–L2 (Assumption A1 — Bıçakçı). Target at Day 100: L2→L3 for combined estate.
General Knowledge Flags | ⚠ A6: RAG threshold numbers = group proposals; ⚠ SMCR Sup 15.3 = anticipated (Kok Day 3 Sess 2, Slide p.15); ⚠ GDPR Art. 28, 46 = general knowledge (obligation is course-grounded); ⚠ EU AI Act Art. 43 = general knowledge (obligation is course-grounded). Flagged inline throughout.; ⚠ NIST CSF 2.0 sub-function codes (GV.RR, GV.RM, GV.OC, ID.AM, ID.RA, ID.SC, DE.CM, PR.AA, RS.MA, RC.RP) = general knowledge from NIST CSF 2.0 document — course covers six top-level functions only (Govern, Identify, Protect, Detect, Respond, Recover per EAIRM Glossary and Framework p.14). Sub-function codes are accurate and cited as standards fluency per Brief Slides Closing ('move fluently between named standards').
Cross-Reference | B1 Risk Register IDs (GR-01 to GR-12) cited in each initiative. Standards from Standards & Controls doc and EAIRM Framework. Board pack linkage to G6 (Deliverable A).
Date | May 2026
EAIRM MATURITY MODEL — Framework p.12 (Source: EAIRM Framework, Layer 5)
Level & Name | Description · Standards Benchmark · B3 Position
L1 — Ad Hoc | AI risks managed reactively. No formal AI risk framework. Standards Benchmark: No formal standards adopted. Gap analysis not yet conducted. B3 Position: LumaPay starting point (confirmed: Bıçakçı — 'partial documentation, fragile lifecycle controls'). Assumption A1.
L2 — Aware | AI risk recognised. Initial policies drafted, governance roles being defined. Execution inconsistent. Standards Benchmark: Gap analysis completed against NIST AI RMF and EU AI Act. ISO 31000 applied. MITRE ATLAS reviewed. B3 Position: Target at end of Phase 1 (Days 1–30). LumaPay exits L1 when RACI, inventory, and appetite statement are in place.
L3 — Structured | Formal AI risk register in place. Lifecycle controls defined. Three Lines of Defence operating. Regular board reporting. Standards Benchmark: NIST AI RMF four functions implemented. ISO/IEC 42001 mapped. NIST CSF 2.0 integrated. EU AI Act compliance roadmap in place. DORA addressed. B3 Position: Target at end of Phase 2–3 (Days 60–100). Combined entity milestone. ISO/IEC 42001 gap analysis complete (R-M02); AIMS implementation plan published (R-O06).
L4 — Integrated | AI risk fully embedded in ERM. Automated monitoring, cross-domain risk correlation, board dashboard operational. Standards Benchmark: Full cross-mapping NIST AI RMF/CSF/ISO/IEC 42001/EU AI Act. Automated metrics per ISO/IEC 23894. External audit underway. MITRE ATLAS in threat intelligence. B3 Position: Aspirational milestone beyond Day 100. Board dashboard (R-O01) and quarterly review (R-O05) begin the path to L4.
L5 — Adaptive | Continuous learning from incidents. Predictive risk indicators. Framework evolves with technology. Standards Benchmark: Contributes to standards development. Real-time regulatory monitoring. Red-teaming via MITRE ATLAS + OWASP LLM. Continuous improvement per ISO/IEC 42001 Cl.10. B3 Position: Long-term institutional target for Nordhaven group — beyond this roadmap's scope.

## B3 Integration Roadmap
B3 — 100-DAY AI INTEGRATION ROADMAP · Nordhaven–LumaPay · Governance & Standards
Initiative ID | Initiative Title | Description | Phase | Days | NIST AI RMF Function(s) | NIST CSF 2.0 Function(s) | Maturity Level (Current → Target) | Dependencies (Initiative IDs) | Milestone / Done Criterion | Proposed Owner | Standards Reference | B1 Risk Register Cross-ref | Status | Course Source / Citation
PHASE 1 — GOVERN: ESTABLISH (Days 1–30) · NIST AI RMF: GOVERN · ISO/IEC 42001 Cl.4–5 · Maturity: L1 → L2 (Ad Hoc → Aware) · Kok, Day 3 Sess 2 (Workstream 1: Inventory/Agent Cards — Slide p.36)
R-G01 | Appoint AI Governance Accountability Owner | Appoint a named SMF-designated individual as the AI governance accountability owner for the combined Nordhaven-LumaPay AI estate. This is the foundational action without which no other governance initiative functions. Nordhaven inherits full regulatory accountability from Day 1 (80% acquisition — Submission Guidance). Must be in place AT close, not after. | 1 | Days 1–5 | GOVERN (GOVERN — Accountability structures; context, culture, policy, roles) | Govern (GV.RR — Roles and responsibilities for AI risk oversight) | L1 → L2 (Ad Hoc → Aware) | None (Day 1 prerequisite — blocks all other initiatives) | Named individual confirmed in role. Announcement to combined entity. Board-level accountability documented. Interim governance structure communicated to all LumaPay department heads. | Group Board / Group CRO (nomination) Named SMF-designated role (execution) | ISO/IEC 42001 Cl.5 (Leadership) UK Corporate Governance Code (board accountability) NIST AI RMF GOVERN 2 EAIRM §5.1 (Board Accountability) ⚠ SMCR Sup 15.3 = anticipated (Kok Day 3 Sess 2, Slide p.15) | GR-01, GR-07 | Not Started | Bıçakçı, Day 5 Sess 3 ('if you can't name an accountable owner...'); Submission Guidance (80% governance responsibility); Kok, Day 3 Sess 2, Slide p.15 (SMCR anticipated); EAIRM §5.1
R-G02 | Shadow AI Discovery Exercise | Execute structured shadow AI discovery across all LumaPay business units. Mandatory disclosure from all department heads. All systems triaged against EU AI Act Art. 6–7 classification. Shadow AI is 'structurally unavoidable without active discovery controls' (Manikam, Day 4 Sess 1). No other governance action can be complete until the full AI estate is known. Inventory feeds into R-G03 (RACI) and R-G05 (Registry). | 1 | Days 1–14 | MAP (MAP 1 — Categorise AI system; MAP 3 — Identify risks associated with system) | Identify (ID.AM — AI asset management and inventory) | L1 → L2 (Ad Hoc → Aware) | R-G01 (Accountability owner must authorise mandatory disclosure to business units) | AI asset inventory complete — all systems documented with: purpose, owner, lifecycle stage, risk tier (EU AI Act). Any undiscovered systems flagged Critical. Inventory signed off by Group CRO. Input to R-G03 and R-G05. | AI Governance Function (2nd Line — lead) Business Unit Heads (1st Line — mandatory disclosure) | NIST AI RMF MAP ISO/IEC 42001 Cl.4 (Context — understand the organisation) EU AI Act Art. 6–7 (classification) NIST CSF 2.0 Identify | GR-02 | Not Started | Bıçakçı, Day 5 Sess 3; Manikam, Day 4 Sess 1 (shadow AI definition) & (discovery controls structurally unavoidable); Kok, Day 3 Sess 2 (agent inventory using agent cards, Slide p.36 — Weeks 1–4)
R-G03 | Establish Interim RACI — All Four Systems, All Six Lifecycle Stages | Establish an interim RACI covering all four LumaPay AI systems across all six lifecycle stages (Design and Intent through Retirement). Per Kok, the RACI table shows '60% of agent governance lives in Continuous Monitor' (Slide p.14). Must specify: who approves deployments, who owns the risk register, how escalation paths function during transition. Board-approved by end of Week 4 per Kok 90-day plan (Slide p.36). | 1 | Days 7–28 | GOVERN (GOVERN — Accountability structures, decision rights framework) | Govern (GV.RR — Roles and responsibilities; GV.OC — Organisational context) | L1 → L2 (Ad Hoc → Aware) | R-G01 R-G02 (partial — need inventory to identify all systems for RACI coverage) | Published RACI table: all four systems × six lifecycle stages × RACI roles. Named Responsible, Accountable, Consulted, Informed for each cell. Group CRO named Accountable for combined estate. Board sign-off obtained. | AI Governance Function (2nd Line — draft) Group CRO (Accountable) Board Risk Committee (approve) | NIST AI RMF GOVERN 2 (accountability structures) ISO/IEC 42001 Cl.5 (Leadership — roles, responsibilities, authorities) RACI Model (EAIRM Glossary §B) AI Lifecycle (EAIRM Glossary §A — six stages) Kok, Day 3 Sess 2, Slide p.14 (RACI table — lifecycle governance) | GR-01, GR-07 | Not Started | Kok, Day 3 Sess 2, Slide p.14 ('60% of agent governance lives in Continuous Monitor') & Slide p.36 (board-approved by end of Week 4); Brief Slides (Deliverable A — 100-Day Plan: 'who approves model deployments, who owns the risk register'); NIST AI RMF GOVERN 2; EAIRM §5.1
R-G04 | Draft Unified AI Risk Appetite Statement | Draft and obtain board approval for a unified AI Risk Appetite Statement addressing all five substrate properties (opacity, autonomy, dependency, drift, scale asymmetry) with LIMIT/CAUTION/TARGET bands. Statements must be 'defensible to regulators' (Bıçakçı). Autonomy is the dominant dimension for AutoUnderwriter Agent and LumaAssist Chat (Kok, Day 3 Sess 2, Slide p.18). Target: board-approved by end of Week 4 per Kok's 90-day plan. | 1 | Days 14–28 | GOVERN (GOVERN — Risk appetite, AI risk culture, organisational policies) | Govern (GV.RM — Enterprise risk management strategy, risk appetite) | L1 → L2 (Ad Hoc → Aware) | R-G01 R-G03 (RACI must identify who approves appetite statement) | Board-approved AI Risk Appetite Statement published. LIMIT/CAUTION/TARGET thresholds defined for all five substrate properties. Statement recorded as ISO/IEC 42001 Cl.5 leadership commitment artefact. Communicated to all LumaPay department heads. | Group CRO (drafting) Board Risk Committee (approval) | ISO 31000 (risk appetite definition) ISO/IEC 42001 Cl.5 (Leadership — AI policy) NIST AI RMF GOVERN (risk appetite framework) COSO ERM EAIRM §5.1 (AI risk appetite & tolerance) ⚠ LIMIT/CAUTION/TARGET = BCG-originated (Kok Day 3 Sess 2, Slide p.19) | GR-01, GR-04 (Autonomy LIMIT) | Not Started | Bıçakçı, Day 5 Sess 3 ('defensible to regulators'); Kok, Day 3 Sess 2 (six-dimension appetite, Slides pp.18–19; board-approved end of Week 4, Slide p.36); EAIRM §5.1; ⚠ LIMIT/CAUTION/TARGET = BCG-originated (not in EAIRM Glossary)
R-G05 | Establish Unified AI Asset Registry | Populate and publish the unified AI Asset Registry for the combined entity. Covers all systems identified in R-G02. Each entry uses standardised agent card fields: purpose, ownership, controls status, risk tier (L1–L5 per Kok's capability classification matrix, Slide p.25), deployment status, lifecycle stage, and named owner per lifecycle stage. Per EAIRM §10.1, the AI Risk Register/Registry is the first of four governance decision artefacts. Bıçakçı requires 'who owns the unified AI registry' to be defined. | 1 | Days 7–28 | MAP + GOVERN (MAP — Characterise AI systems; GOVERN — Policies, roles, accountability) | Identify (ID.AM — Asset management, AI asset inventory) | L1 → L2 (Ad Hoc → Aware) | R-G02 (discovery exercise generates initial inventory) | Registry published — all known AI systems documented with: name, purpose, named owner, risk tier, EU AI Act classification, deployment status, lifecycle stage. Registry accessible to Governance, Risk, and Compliance functions. Nominated registry owner confirmed. | AI Governance Function (2nd Line — maintain) IT/Data Architecture (1st Line — populate) Nominated Registry Owner | NIST AI RMF MAP ISO/IEC 42001 Cl.4 (Context — understand AI systems) EAIRM §10.1 (AI Risk Register as governance decision artefact) Kok, Day 3 Sess 2, Slide p.25 (L1–L5 capability classification) | GR-02, GR-01 | Not Started | Kok, Day 3 Sess 2 (agent inventory using agent cards, Slide p.36 — Weeks 1–4; L1–L5 capability classification matrix, Slide p.25); Bıçakçı, Day 5 Sess 3 ('who owns the unified AI registry'); EAIRM §10.1
PHASE 2 — MAP + MEASURE: CLASSIFY & EVALUATE (Days 31–60) · NIST AI RMF: MAP + MEASURE · EU AI Act Art. 6–7, 9, 10; ISO/IEC 42001 Cl.4–9 · Maturity: L2 → L3 (Aware → Structured, partial) · Kok, Day 3 Sess 2 (Workstream 2: Decision Rights Matrix — Slide p.36)
R-M01 | EU AI Act Risk Classification Exercise — All Systems | Formally classify all in-scope AI systems against EU AI Act Art. 6–7 risk tiers. LumaCredit-EU is confirmed Annex III high-risk (Brief Slides). Classification of LumaAssist Chat, AutoUnderwriter Agent, and FraudShield (deployer obligations for third-party) must be formally assessed. Includes systems identified in R-G02 discovery. Output feeds R-M02 (ISO/IEC 42001 gap analysis) and R-O03 (conformity assessment). NIST AI RMF MAP 1.5 cited in Brief Slides as standards fluency example. | 2 | Days 31–45 | MAP (MAP 1 — Categorise AI system and context; MAP 1.5 — Categorise per regulatory requirements) | Identify (ID.RA — Risk assessment per system; ID.AM — Asset classification update) | L2 → L3 (Aware → Structured, partial) | R-G02, R-G05 (Full inventory and registry must be in place) | EU AI Act risk classification register published: each system assigned risk tier with supporting legal analysis. LumaCredit-EU Annex III confirmed in writing. Legal counsel sign-off. Register stored in AI Asset Registry (R-G05). | Head of AI Assurance Legal / AI Governance Function | EU AI Act Art. 6–7 (risk classification — Standards & Controls doc p.3) EU AI Act Art. 9 (triggers for Annex III risk management system) NIST AI RMF MAP 1.5 (Brief Slides, Closing — standards fluency example) | GR-02, GR-03 | Not Started | Brief Slides ('LumaCredit-EU — Classified as high-risk under EU AI Act (Annex III)'); Bıçakçı, Day 5 Sess 3; Standards & Controls doc p.3 (EU AI Act Art. 6–7); Kok, Day 3 Sess 2 (L1–L5 capability classification, Slide p.25); Brief Slides Closing (NIST AI RMF MAP 1.5 as standards fluency example)
R-M02 | ISO/IEC 42001 AIMS Gap Analysis — LumaPay vs Cl.4–9 | Conduct a clause-by-clause gap analysis of LumaPay's AI Management System posture against ISO/IEC 42001 (Cl.4 Context through Cl.10 Improvement). LumaPay confirmed L1–L2 — cannot demonstrate compliance with any clause (Assumption A1). Gap analysis is the prerequisite for R-O06 (AIMS Implementation Plan) and the L2→L3 bridge. EAIRM §10.1 uses ISO/IEC 42001 as the implementing standard for the AI governance operating model. | 2 | Days 31–55 | MAP + GOVERN (MAP — Context, standards characterisation; GOVERN — Policies, management system) | Identify (ID.RA — Risk assessment vs. AIMS requirements); Govern | L2 → L3 (Gap analysis = Aware → Structured bridge) | R-G01, R-G03, R-G05 | Gap analysis report published: Cl.4–10 coverage, evidence vs. gap for each clause, prioritised remediation actions. Submitted to Group CRO and ISO/IEC 42001 Implementation Lead. Report feeds R-O06 Implementation Plan. | AI Governance Function (2nd Line) Nominated ISO/IEC 42001 Implementation Lead | ISO/IEC 42001 Cl.4–10 (all clauses — Standards & Controls doc p.2) NIST AI RMF GOVERN EAIRM §9 (Maturity Model, Framework p.12) EAIRM §10.1 | GR-10 | Not Started | Standards & Controls doc p.2 (ISO/IEC 42001 — all clauses); EAIRM Framework §9 (Maturity Model p.12 — L3 benchmark: 'ISO/IEC 42001 management system mapped'); EAIRM §10.1; Bıçakçı, Day 5 Sess 3 (LumaPay fragile lifecycle controls)
R-M03 | Cross-Border Data Flow Mapping — GDPR / UK DPA | Map all EU–UK–US data flows for the four in-scope AI systems. Confirm or establish cross-border transfer mechanisms for all EU→US transfers. Audit Data Processing Agreements for all cloud providers. Bıçakçı confirms data flowing to US-hosted cloud regions 'raising immediate questions on the GDPR, UK DPA'. Transfer mechanism status is unconfirmed pre-close and must be resolved in this phase. | 2 | Days 31–55 | MAP (MAP — Data provenance, data flow characterisation, dependency mapping) | Identify (ID.AM — Data assets and flows); Govern | L2 → L3 (Aware → Structured) | R-G02, R-G05 (Inventory must be complete to identify all data flows) | Data flow map published: each system has confirmed transfer mechanism (or gap with remediation timeline). DPA audit complete for all cloud processors. DPO sign-off obtained. Any gaps escalated to Legal with 30-day remediation target. | Data Protection Officer / Group Privacy Function Head of Vendor Governance (cloud DPAs) | GDPR Art. 5 (data accuracy — Standards & Controls doc p.3) UK DPA 2018 (Standards & Controls doc p.3) ISO/IEC 27701 (privacy governance — Standards & Controls doc p.2) ISO/IEC 42001 Cl.4 (Context — external legal requirements) ⚠ GDPR Art. 28, 46 = general knowledge (DPA/transfer obligation is course-grounded: Bıçakçı) | GR-09 | Not Started | Bıçakçı, Day 5 Sess 3 ('data will start flowing into US-hosted cloud regions, raising immediate questions on the GDPR, UK DPA'); Standards & Controls doc p.3 (GDPR Art. 5; UK DPA 2018; ISO/IEC 27701); DD Artefact 4 (board pack)
R-M04 | Vendor Contract Audit — FraudShield and Foundation Model Providers | Complete a structured vendor contract audit for FraudShield (change-of-control and non-assignability clauses — confirmed unreviewed pre-close) and all foundation model providers (LumaAssist Chat, AutoUnderwriter Agent). FraudShield risk is CRITICAL in GR-06 — loss of fraud detection capability at close if change-of-control triggered. Kok's AdvisorBot case demonstrates how a vendor foundation-model update produces a compound risk event spanning all three EAIRM lenses (Day 3 Sess 2, Slides pp.34–35). | 2 | Days 31–50 | MAP (MAP — Dependency mapping, third-party system characterisation; supply chain risk) | Identify (ID.SC — Supply chain risk management; ID.RA — Vendor risk assessment) | L2 → L3 (Aware → Structured) | R-G01, R-G03 | Vendor contract audit complete. FraudShield: change-of-control status confirmed in writing, interim fallback plan in place. Foundation model providers: SLAs reviewed against DORA Art. 30 requirements, concentration risk documented. Legal sign-off. Audit report submitted to AI Governance Function. | Head of Vendor Governance / Procurement Legal | DORA Art. 28 (vendor assessment — mandatory, Standards & Controls doc p.3) DORA Art. 29 (ICT concentration risk assessment — Standards & Controls doc p.3) DORA Art. 30 (contractual safeguards — Standards & Controls doc p.3) ISO/IEC 27036 (supplier relationships — cited in Brief Slides for FraudShield) | GR-06 | Not Started | Brief Slides ('FraudShield — governed by ISO/IEC 27036 and DORA'); Bıçakçı, Day 5 Sess 3 (change-of-control risk at close); Kok, Day 3 Sess 2 (AdvisorBot compound risk — vendor update, Slides pp.34–35; monoculture/coupling, Slide p.6); Standards & Controls doc p.3 (DORA Art. 28–30)
R-M05 | Model Card Documentation — All Four In-Scope Systems | Complete model cards for all four in-scope AI systems. For LumaCredit-EU (Annex III high-risk), model cards are a prerequisite for EU AI Act Art. 9 compliance and for R-O03 (conformity assessment). For AutoUnderwriter Agent, model card defines the system boundaries required for HITL gate design (R-M06). Absence confirmed pre-close (Bıçakçı). Each card documents: purpose, training data governance, performance metrics, known limitations, explainability approach, intended use, out-of-scope uses, named owner. | 2 | Days 31–55 | MAP + MEASURE (MAP — Characterise AI system; MEASURE — Establish performance baseline, explainability evidence) | Identify (ID.RA — Risk assessment per system; ID.AM — Asset documentation) | L2 → L3 (Aware → Structured) | R-G02, R-G05 (Inventory and registry must identify all systems) | Model card complete for each of the four in-scope systems. Each card has named owner, performance metrics, explainability approach, and intended vs. out-of-scope use documentation. Stored in AI Asset Registry. LumaCredit-EU model card submitted to EU AI Act Compliance Lead for conformity assessment (R-O03). | Head of AI Assurance (2nd Line) AI System Owners / Data Scientists (1st Line) | EU AI Act Art. 9 (risk management system documentation — Standards & Controls doc p.3) ISO/IEC 42001 Cl.8 (Operation) NIST AI RMF MAP EAIRM §10.1 (AI Risk Register as decision artefact) | GR-03, GR-04 GR-05 | Not Started | Bıçakçı, Day 5 Sess 3 ('model cards absent or incomplete'); Manikam, Day 4 Sess 1 (System Cards analogous to model cards); Standards & Controls doc p.3 (EU AI Act Art. 9); DD Artefact 2 (board pack)
R-M06 | HITL Gate Design — AutoUnderwriter Agent | Design a documented Human-in-the-Loop (HITL) gate for all regulated decisions made by AutoUnderwriter Agent. This phase covers DESIGN ONLY — implementation is Phase 3 (R-O02). Manikam confirms 'in regulated environments, all other high-risk decisions require HITL' (Day 4 Sess 1). Design specifies: human reviewer role, decision categories requiring HITL, escalation triggers, audit trail mechanism, and scope of autonomous vs. HITL-governed operations. | 2 | Days 45–60 | GOVERN (GOVERN — Decision rights for AI deployment; autonomy controls) | Govern (GV.RR — Roles in AI oversight); Protect (safeguards design for agentic deployment) | L2 → L3 (Aware → Structured) | R-M05 (AutoUnderwriter model card defines system boundaries for HITL scope) R-G03 (RACI — who performs the human review) | HITL gate design document published and reviewed by Head of AI Assurance. Specifies: human reviewer role, decision categories, escalation path, audit trail mechanism. Document ready for technical implementation in R-O02. | Head of AI Assurance (2nd Line) AutoUnderwriter Agent System Owner (1st Line) | EU AI Act Art. 14 (human oversight measures for high-risk AI — Standards & Controls doc p.3) NIST AI RMF GOVERN 2 (decision rights) ISO/IEC 42001 Cl.8 (Operation — deployment controls) | GR-04 | Not Started | Manikam, Day 4 Sess 1 (HITL mandatory for regulated environments — 'all other high-risk decisions require HITL'); Brief Slides ('AutoUnderwriter Agent — governance controls least mature'); EU AI Act Art. 14 (Standards & Controls doc p.3)
R-M07 | AI System Performance Baselines and KRI Measurement Framework | Establish quantitative performance baselines and a KRI measurement methodology for all four in-scope AI systems following model card completion (R-M05). For LumaCredit-EU (Annex III high-risk): configure drift detection thresholds (prediction drift, data drift, input data quality), define explainability measurement approach, and document accuracy and fairness baselines. Per EAIRM §10.1: 'Model drift — NIST AI RMF MEASURE-2.6, ISO/IEC 23894 §6.3, EU AI Act Art. 9(9)'. MEASURE outputs directly feed the Board Risk Dashboard (R-O01) and quarterly KRI review (R-O05). Monitoring must be continuous, not one-time (Manikam, Day 4 Sess 1). | 2 | Days 50–60 | MEASURE (MEASURE 2 — AI system and components evaluated, tested, validated; MEASURE 2.6 — AI system performance monitoring; quantitative basis for risk appetite monitoring per EAIRM Framework p.10) | Detect (DE.CM — Continuous monitoring metrics established and configured) Identify (ID.RA — Risk measurement per NIST AI RMF Playbook Measure 1.1) | L2 → L3 (MEASURE function implemented = L3 Structured benchmark: 'NIST AI RMF four functions implemented' — EAIRM Framework p.12) | R-M05 (Model cards must be complete — provide system baselines and performance documentation) | Performance baselines documented for all four systems. Drift detection thresholds configured for LumaCredit-EU (prediction drift, data drift, input quality). KRI measurement framework operational and ready to populate R-O01 dashboard. Standards traceability record per EAIRM §10.1 submitted to Head of AI Assurance. | Head of AI Assurance (2nd Line) Data Scientists / MLOps (1st Line — configure) Nominated KRI Framework Lead | ISO/IEC 23894 (AI risk monitoring — Standards & Controls doc p.2) NIST AI RMF MEASURE 2.6 (AI system performance monitoring — EAIRM §10.1) ISO/IEC 5259 (data quality metrics — Standards & Controls doc p.2) ISO/IEC 42001 Cl.9 (Performance Evaluation) EU AI Act Art. 9 (risk management system — continuous monitoring obligation) EU AI Act Art. 15 (accuracy, robustness, cybersecurity — Standards & Controls doc p.3) | GR-03, GR-08 GR-04 | Not Started | EAIRM Framework §10.1 ('Model drift — NIST AI RMF MEASURE-2.6, ISO/IEC 23894 §6.3, EU AI Act Art. 9(9)'); Yemi, Day 4 Sess 2 (MEASURE function: NIST AI RMF clause 5.3 & Playbook Measure 1.1, 2.4 — Master Reference §1.3 & §1.7; drift detection: data drift, prediction drift, input data quality — §1.7); Manikam, Day 4 Sess 1 ('monitoring is never one-time'); Standards & Controls doc p.2 (ISO/IEC 23894; ISO/IEC 5259)
PHASE 3 — MANAGE: OPERATE (Days 61–100) · NIST AI RMF: MANAGE + MEASURE · NIST CSF 2.0: Detect / Respond · Maturity: L3 → L4 (Structured → Integrated, milestone) · Kok, Day 3 Sess 2 (Workstream 3: Tabletop on real use case — Slide p.36)
R-O01 | Board Risk Dashboard — First Operational Version | Deploy first operational version of the Board Risk Dashboard per EAIRM §10.3. Eight-panel structure per Kok Day 3 Sess 2 ('eight-panel board dashboard first version live by week 10', Slide p.36). Dashboard shows: KRI status across four systems (from B1 register KRIs), maturity level progress (L1→L3), EU AI Act compliance status per system, RACI coverage, and vendor audit completion. First monthly KRI review cycle initiated using Yemi's 40-KRI framework (Day 4 Sess 2, Slides p.47). | 3 | Days 61–80 | MANAGE + MEASURE + GOVERN (MANAGE — Monitor AI system risks; MEASURE — KRI metrics displayed on dashboard, quantitative basis for risk appetite monitoring per EAIRM Framework p.10; GOVERN — Board reporting and accountability) | Govern (GV.OC — Org context); Detect (DE.CM — Continuous monitoring) | L3 → L4 (Structured → Integrated milestone) | R-G04 (appetite defines dashboard thresholds) R-G03 (RACI defines recipients) All Phase 2 initiatives (provide data for dashboard panels) | Dashboard published and presented at first Board Risk Committee meeting. Monthly KRI review cycle initiated (Yemi's cadence). Named dashboard owner. All eight panels operational and populated. Senior leadership briefed on KRI status. | Group CRO (Accountable) AI Governance Function (2nd Line — populate and maintain) Board Risk Committee (recipient) | NIST AI RMF MANAGE (monitoring) NIST CSF 2.0 Detect / Govern EAIRM §10.3 (Board Risk Dashboard artefact) ISO/IEC 42001 Cl.9 (Performance Evaluation) Kok, Day 3 Sess 2 (Reporting — Choice 3; Slides pp.12–35) | GR-01, GR-07 (all GR entries feed dashboard) | Not Started | Kok, Day 3 Sess 2 ('eight-panel board dashboard first version live by week 10', Slide p.36; Choice 3 Reporting, Slides pp.12–35); Yemi, Day 4 Sess 2, Slides p.47 (40-KRI framework); EAIRM §10.3; Bıçakçı
R-O02 | HITL Controls Implementation — AutoUnderwriter Agent | Implement the HITL gate designed in R-M06. Deploy human review procedure, configure AutoUnderwriter Agent to require HITL for all regulated decisions, establish audit trail, test with real-world use cases. This is a LIMIT condition per the risk appetite (GR-04): AutoUnderwriter Agent must not make regulated decisions without HITL from Day 1 of combined entity operations. KRI AI-06 (% of high-risk AI use cases without HITL controls) must reach 0%. | 3 | Days 61–85 | MANAGE (MANAGE — Deploy with controls; enforce decision rights) GOVERN (Decision rights enforcement) | Protect (PR.AA — Access control for AI decisions) Detect (DE.CM — Monitor HITL compliance) | L3 → L4 (Structured → Integrated) | R-M06 (HITL design must be complete) R-O01 (dashboard ready to monitor KRI AI-06) | HITL gate live in production. First HITL-reviewed decision recorded and logged with audit trail. Head of AI Assurance sign-off. KRI AI-06 (% of high-risk AI use cases without HITL) = 0% confirmed in dashboard. Implementation verified against EU AI Act Art. 14 checklist. | Head of AI Assurance (2nd Line) AutoUnderwriter Agent System Owner (1st Line) | EU AI Act Art. 14 (human oversight measures — Standards & Controls doc p.3) NIST AI RMF MANAGE NIST AI RMF GOVERN 2 (decision rights enforcement) ISO/IEC 42001 Cl.8 (Operation) | GR-04 | Not Started | Manikam, Day 4 Sess 1 (HITL mandatory for regulated decisions); Brief Slides ('governance controls least mature' for agentic); EU AI Act Art. 14 (Standards & Controls doc p.3); Yemi, Day 4 Sess 2, Slides p.47 (KRI AI-06)
R-O03 | LumaCredit-EU EU AI Act Conformity Assessment — Initiation | Initiate the EU AI Act Art. 9 risk management system conformity assessment for LumaCredit-EU (Annex III high-risk). The full assessment will take 6–12 months (beyond Day 100) but initiation — appointment of lead, scope definition, first technical review of Art. 9 requirements — must occur in Phase 3. Bıçakçı flags 'conformity assessments' as a pre-close question and uses EU AI Act Art. 9 as the standards fluency anchor. | 3 | Days 61–90 | MAP + MEASURE (MAP — Complete characterisation; MEASURE — Begin evaluation against conformity requirements) | Identify (ID.RA — Regulatory risk assessment per EU AI Act) Govern | L2 → L3 (Initiating conformity programme = L3 Structured milestone) | R-M01 (EU AI Act classification confirmed) R-M05 (Model card for LumaCredit-EU complete) | Conformity assessment initiated: lead appointed, scope defined, first technical review of EU AI Act Art. 9 requirements complete. Assessment timeline agreed (target: 6–12 months post-Day 100). EU AI Act compliance programme formally opened. Documented in AI Asset Registry. | Head of AI Assurance Nominated EU AI Act Compliance Lead Legal | EU AI Act Art. 9 (risk management system — Standards & Controls doc p.3) EU AI Act Art. 62 (serious incident reporting — 15-day obligation begins at deployment) ISO/IEC 42001 Cl.8 (Operation) ⚠ EU AI Act Art. 43 (conformity assessment article number = general knowledge; obligation is course-grounded per Bıçakçı) | GR-03 | Not Started | Bıçakçı, Day 5 Sess 3 ('conformity assessments') & (EU AI Act Art. 9 standards fluency anchor); Standards & Controls doc p.3 (EU AI Act Art. 9, Art. 62); G6 board pack (Days 61–100)
R-O04 | Escalation Protocol — Design, Publish, Test | Design, publish, and test the AI Risk Escalation Protocol per EAIRM §10.4. Must specify: what constitutes an AI risk event, notification requirements (EU AI Act Art. 62 = 15-day serious incident; DORA Art. 19 = major ICT incident), authority to halt or constrain a system, and reporting timelines. Kok's Choice 5 (Escalation, Day 3 Sess 2) provides the operating model template. Protocol must be tested through a tabletop exercise on a real use case (Kok, Slide p.36, Weeks 11–12). Post-tabletop lessons incorporated. | 3 | Days 61–90 | MANAGE + GOVERN (MANAGE — Incident response, escalation; GOVERN — Accountability for escalation paths) | Respond (RS.MA — Incident management, escalation) Recover (RC.RP — Recovery planning) | L3 → L4 (Structured → Integrated milestone) | R-G03 (RACI — who escalates to whom) R-G04 (appetite defines escalation triggers) R-O01 (dashboard — detects threshold breach that triggers escalation) | Escalation Protocol published. First tabletop exercise completed on a real LumaPay use case (e.g. AutoUnderwriter Agent out-of-scope decision scenario per Kok's AdvisorBot case structure). Post-tabletop lessons documented and protocol updated. Group CRO and Named SMF briefed. | AI Governance Function (2nd Line) Group CRO (Accountable) Integration Programme Director | DORA Art. 11 (ICT incident management — Standards & Controls doc p.3) DORA Art. 19 (major ICT incident reporting — Standards & Controls doc p.3) EU AI Act Art. 62 (serious incident — 15-day notification) NIST CSF 2.0 Respond / Recover EAIRM §10.4 (Incident and Escalation Protocol artefact) | GR-11, GR-01 | Not Started | Kok, Day 3 Sess 2 (Choice 5 — Escalation; first tabletop on real use case, Slide p.36, Weeks 11–12; AdvisorBot scenario as template, Slides pp.34–35); EAIRM §10.4; Standards & Controls doc p.3 (DORA Art. 11, 19; EU AI Act Art. 62)
R-O05 | First Quarterly Governance Review | Conduct the first formal quarterly AI governance review confirming: RACI is operating (not just documented), all Phase 1–2 milestones are complete or on track, KRI dashboard is cycling, escalation protocol has been tested, and progress against ISO/IEC 42001 gap analysis is evidenced. Yemi's monthly KRI review cycle provides the cadence model ('Information Security Governance meetings with senior leadership, with documented observations, actions, and owners' — Day 4 Sess 2, Master Reference §5.1). This review establishes the governance rhythm sustaining the combined entity beyond Day 100. | 3 | Days 90–100 | MANAGE + MEASURE + GOVERN (MANAGE — Ongoing risk monitoring and review; MEASURE — Evaluate KRI performance against baselines and appetite thresholds established in R-M07; GOVERN — Continuous improvement, accountability) | Govern (GV.RM — Risk management strategy review) Detect (DE.CM — Monitoring) | L3 → L4 (Quarterly review cycle = L3 Structured → L4 Integrated bridge) | All Phase 1 and Phase 2 initiatives R-O01 (dashboard operational) R-O04 (escalation protocol tested) | First quarterly governance review report published. Named action owner per item. Board Risk Committee briefed. KRI dashboard reviewed with senior leadership. Formal record of review per ISO/IEC 42001 Cl.9 (Performance Evaluation). Review date for Q2 confirmed. | Group CRO (Accountable) AI Governance Function (2nd Line — organise) Board Risk Committee (recipient) | ISO/IEC 42001 Cl.9 (Performance Evaluation — monitoring, measurement, internal audit — Standards & Controls doc p.2) NIST AI RMF MANAGE (ongoing monitoring) NIST CSF 2.0 Govern ISO 31000 (risk monitoring and review) EAIRM §10.3–10.4 | All GR entries (Review monitors all B1 risks) | Not Started | Yemi, Day 4 Sess 2 (monthly KRI review cycle; Information Security Governance meetings with senior leadership); EAIRM §10.3–10.4; Standards & Controls doc p.2 (ISO/IEC 42001 Cl.9); Kok, Day 3 Sess 2 (Choice 3 — Reporting: board dashboard cadence)
R-O06 | ISO/IEC 42001 AIMS Implementation Plan — Published | Publish the ISO/IEC 42001 AI Management System implementation plan, translating the gap analysis (R-M02) into a structured remediation programme covering Cl.4–Cl.10. Full AIMS certification is a 12–24 month programme beyond Day 100 — but having the plan published and board-approved by Day 100 is the L3 Structured milestone ('ISO/IEC 42001 management system mapped' — EAIRM Maturity Model, Framework p.12). This is also EAIRM §10.1 — the AI governance operating model implementing standard. | 3 | Days 75–100 | GOVERN + MANAGE (GOVERN — Establish AI risk management programme; MANAGE — Implement controls per plan) | Govern (GV.OC — Organisational context for risk management) | L3 → L4 (AIMS plan published = L3 milestone; full implementation achieves L4) | R-M02 (gap analysis complete — plan cannot be built without it) R-G01, R-G03, R-G04 | ISO/IEC 42001 AIMS Implementation Plan published and board-approved. Timeline for achieving compliance against each clause (Cl.4–10) with named owner per clause. Nominated ISO/IEC 42001 Implementation Lead confirmed. Plan submitted to Board Risk Committee alongside first quarterly governance review (R-O05). | AI Governance Function (2nd Line — lead) Group CRO (Accountable) Nominated ISO/IEC 42001 Implementation Lead | ISO/IEC 42001 Cl.4–10 (all clauses — Standards & Controls doc p.2) NIST AI RMF GOVERN EAIRM §9 (Maturity Model — Framework p.12 — L3 benchmark: 'ISO/IEC 42001 management system mapped') EAIRM §10.1 (AI governance operating model implementing standard) | GR-10, GR-01 GR-03 | Not Started | Standards & Controls doc p.2 (ISO/IEC 42001 — all clauses); EAIRM Framework §9 (Maturity Model p.12 — L3: 'NIST AI RMF four functions implemented; ISO/IEC 42001 management system mapped'); EAIRM §10.1; Bıçakçı, Day 5 Sess 3
FIELD STRUCTURE NOTES: • Phase structure: G6 board pack (Deliverable A) — Days 1–30 GOVERN / Days 31–60 MAP / Days 61–100 MANAGE. Aligned to Kok, Day 3 Sess 2 (three workstreams — agent inventory Weeks 1–4; decision rights/dashboard Weeks 5–10; tabletop Weeks 11–12, Slide p.36). • Maturity levels: EAIRM five-level model (Framework p.12) — L1 Ad Hoc → L2 Aware → L3 Structured → L4 Integrated → L5 Adaptive. LumaPay starting position L1–L2 (Assumption A1, Bıçakçı ). Target at Day 100: L2→L3 for combined estate. • NIST AI RMF functions: GOVERN, MAP, MEASURE, MANAGE. NIST CSF 2.0 functions: Govern, Identify, Protect, Detect, Respond, Recover. Source: EAIRM Framework p.7–10, p.14 (Standards Cross-Reference Matrix); Standards & Controls doc p.1–2. • Assumptions: A1 (LumaPay L1–L2 maturity — course-grounded); A2 (DORA as group benchmark); A6 (RAG thresholds — structure course-grounded, numbers = group proposals); ⚠ SMCR Sup 15.3 = anticipated (Kok Day 3 Sess 2, Slide p.15 — not yet mandated). All documented in Assumptions Register sheet.

## Assumptions Register
ASSUMPTIONS REGISTER — Deliverable B3 100-Day AI Integration Roadmap
ID | Assumption | What It Is | Course Grounding | Type | Review Flag
A1 | LumaPay governance maturity L1–L2 | LumaPay positioned at 'Ad Hoc to Aware' (L1–L2) on the EAIRM Maturity Model. Drives Phase 1 sequencing — foundational governance structures before classification and monitoring. | Bıçakçı, Day 5 Sess 3 ('partial documentation, fragile lifecycle controls, limited board-level oversight'). EAIRM Maturity Model (Framework p.12). | Course-grounded | Defensible inference — no formal score in brief
A2 | DORA applied as Nordhaven group benchmark to UK entity | DORA formally applies to EU financial entities. Applied as group benchmark for LumaPay. Drives Domain 5 vendor governance initiatives (R-M04). | Bıçakçı flags DORA; EAIRM maps FraudShield to DORA Art. 28–30 (Brief Slides). Nordhaven is EU bank. Authorised by Bıçakçı (Submission Guidance). | Course-grounded | State explicitly — DORA may not bind LumaPay directly as UK entity
A6 | Quantitative RAG threshold numbers | LIMIT/CAUTION/TARGET band structure is course-derived (Kok Day 3 Sess 2, Slide p.19). Specific threshold percentages (e.g. drift >5%) are group proposals authorised by Bıçakçı. | RAG band structure: Kok, Day 3 Sess 2, Slide p.19 (⚠ BCG-originated — not in EAIRM Glossary). Threshold numbers: Submission Guidance (authorised assumptions). | Structure course-grounded; Numbers = group proposals | Threshold numbers must be presented as proposed, not course-stated
A7 | Consumer Duty detailed obligations | FCA/Consumer Duty reference is course-stated (Bıçakçı). Four-outcome framework detail is UK financial services general knowledge. | Bıçakçı; Brief Slides (Regulatory Context: Consumer Duty). Four-outcome detail: general knowledge. | ⚠ General knowledge | Flag in submission — review Consumer Duty detail
SMCR-AI | SMCR-AI requirements are anticipated — not yet mandated | Kok's three anticipated SMCR-AI requirements (named SMF holder, updated SoR, Sup 15.3 AI risk events) are presented in B3 as best-practice governance actions. Not yet formally mandated by FCA. | Kok, Day 3 Sess 2, Slide p.15 (anticipated SMCR-AI). Kok, ('don't wait for SMCR-AI guidance — act now'). Confirms these are not yet in force. | Course-grounded (Kok Day 3 Sess 2); Not yet mandated | Always present as 'anticipated requirement' — never as current FCA mandate
GK-GDPR | GDPR Art. 28 and Art. 46 are general knowledge article numbers | The obligations to have DPAs (Art. 28) and cross-border transfer mechanisms (Art. 46) are course-stated (Bıçakçı). The specific article numbers are not in the Standards & Controls doc or EAIRM Framework article lists. | DPA obligation: Bıçakçı, ('DPAs' named as artefacts to request). Transfer obligation: Bıçakçı. Standards & Controls doc GDPR row covers Art. 5, 22, 32–34 only. | ⚠ Article numbers = general knowledge; Obligation = course-grounded | Applied ⚠ flag in R-M03 Standard Reference. Correct and relevant obligations.
GK-43 | EU AI Act Art. 43 is a general knowledge article number | The conformity assessment obligation for Annex III high-risk systems is course-stated (Bıçakçı). The specific article number Art. 43 is not in the Standards & Controls doc (covers Art. 6–7, 9, 10, 13–14, 15, 62). | Bıçakçı, ('conformity assessments'). Standards & Controls doc p.3 covers EU AI Act at Art. 6–7, 9, 10, 13–14, 15, 62 explicitly. | ⚠ Article number = general knowledge; Obligation = course-grounded | Applied ⚠ flag in R-O03 Standard Reference. Correct and relevant obligation.